## Sheet1
TASK NAME | STATUS | START DATE | DEADLINE | COMMENTS
Project Phase 1 | COMPLETE | 2022-01-24 | 2022-02-21
1st Client Meeting | COMPLETE | 2022-01-26
2nd Client Meeting | COMPLETE | 2022-01-31
3rd Client Meeting | COMPLETE | 2022-02-09
1st Group Meeting | COMPLETE | 2022-02-12
Create UML Use Case Diagrams | COMPLETE | 2022-02-12 | 2022-02-21
Create UML Diagrams | COMPLETE | 2022-02-12 | 2022-02-21
Create Requirements Document | COMPLETE | 2022-02-12 | 2022-02-21
Create Detailed Group/Client Meetings Document | COMPLETE | 2022-02-12 | 2022-02-21
2nd Group Meeting | COMPLETE | 2022-02-16
3rd Group Meeting | COMPLETE | 2022-02-19
4th Group Meeting | COMPLETE | 2022-02-21
Project Presentation for Phase 1 | NOT STARTED | 2022-02-28 | 2022-03-02
Project Phase 2 | NOT STARTED | 2022-02-21 | 2022-03-23
5th Group Meeting | SCHEDULED | 2022-02-24
6th Group Meeting | SCHEDULED | 2022-03-03
7th Group Meeting | SCHEDULED | 2022-03-10
8th Group Meeting | SCHEDULED | 2022-03-17
Project Presentation for Phase 2 | NOT STARTED | 2022-04-04 | 2022-04-06
Final Phase (Complete Project) | NOT STARTED | 2022-03-23 | 2022-05-01
9th Group Meeting | SCHEDULED | 2022-03-31
10th Group Meeting | SCHEDULED | 2022-04-07
11th Group Meeting | SCHEDULED | 2022-04-14
12th Group Meeting | SCHEDULED | 2022-04-21
13th Group Meeting | SCHEDULED | 2022-04-28
Completed Project Presentation | NOT STARTED | 2022-05-02 | 2022-05-04